## UIST TO DO
Software |  | Hardware
Task | Status | Task | Status
make basic reading of pressure values into data structure | done | experiment with servo | done
translate values to motor actions | done | order 5 servos | done
Find the needed commands to control the servo's up and down | done | get puppet and strings | done
integrate the commands to solution | done | get pullies for servos
test with servo | done | set up puppet with strings and servos
test with puppet |  | test with software
improve identifying algorithm |  | build frame for puppet display
map string pulling limits |  | experiment with motor to move entire puppet left and right
identify hand movement for left and right |  | build frame rail for puppet movement
control motor for moving puppet on rail |  | prepare and test plan for disassembly and reassembly of hardware
test with puppet
record movement segment
play movement segment
create UI for record/play menu
make basic virtual puppet display
To consider during construction: servo screws must be accessible
minimize noise from the 5-8 servos all working together..
possible to take apart and put back together
connect hook for a string to hold the puppet

## Sheet1
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
|  |  | 2012-09-13 | 2012-09-14 | 2012-09-15 | 2012-09-16
|  |  | Work on continuous servo movements | Work on continuous servo string pulling
2012-09-17 | 2012-09-18 | 2012-09-19 | 2012-09-20 | 2012-09-21 | 2012-09-22 | 2012-09-23
Hardware setup testing | Hardware setup testing | Hardware setup testing | Test and improve stationary 5 servos puppet movements | Test and improve stationary 5 servos puppet movements
Work on continuous servo string pulling | Work on continuous servo string pulling | Test and improve stationary 5 servos puppet movements |  | Write right/left movement recognition code
2012-09-24 | 2012-09-25 | 2012-09-26 | 2012-09-27 | 2012-09-28 | 2012-09-29 | 2012-09-30
Test and improve stationary 5 servos puppet movements | Test and improve stationary 5 servos puppet movements | Test and improve right/left movements | Test and improve right/left movements | Test and improve right/left movements
Write right/left movement recognition code | Write recording/playing code | Write recording/playing code | Write recording/playing code | Write recording/playing code
2012-10-01 | 2012-10-02 | 2012-10-03 | 2012-10-04 | 2012-10-05 | 2012-10-06 | 2012-10-07
Testing, Recording and playing sequences | Testing, Recording and playing sequences | Testing, Disassembly and assembly | Testing, Disassembly and assembly | Testing, Disassembly and assembly | Testing, Disassembly and assembly | UIST final preperations