## UIST TO DO
Software |  | Hardware
Task | Status | Task | Status
make basic reading of pressure values into data structure | done | experiment with servo | done
translate values to motor actions | done | order 5 servos | done
Find the needed commands to control the servo's up and down | done | get puppet and strings | done
integrate the commands to solution | done | make the servo pull string faster
test with servo | done | set up puppet with strings and servos
test with puppet |  | test with software
improve identifying algorithm |  | build frame for puppet display
map string pulling limits |  | experiment with motor to move entire puppet left and right
identify hand movement for left and right |  | build frame rail for puppet movement
control motor for moving puppet on rail |  | create movement segments
test with puppet |  | prepare and test plan for disassembly and reassembly of hardware
record movement segment
play movement segment
create UI for record/play menu
make basic virtual puppet display